## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint1 | Sprint1 | US001 | Research & Technical understanding | MUST HAVE |  | Sanjana | Completed
Sprint1 | Sprint1 | US002 | System Architecture | MUST HAVE | M1.1 | Sanjana | Completed
Sprint1 | Sprint1 | US003 | Evaluation Architecture | MUST HAVE | M1.2 | Sanjana | Completed
Sprint1 | Sprint1 | US004 | Reference Knowledge Base | MUST HAVE | M1.2 | Sanjana | 3- Completed
Sprint2 | Sprint2 | US005 | Relevance Judge Agent | MUST HAVE | M2.1 | Sanjana | Completed
Sprint2 | Sprint2 | US006 | Accuracy Judge Agent | MUST HAVE | M2.2 | Sanjana | Completed
Sprint2 | Sprint2 | US007 | Hallucination Detection Agent | MUST HAVE | M2.3 | Sanjana | Completed
Sprint2 | Sprint2 | US008 | Milestone 2 Agent Validation | MUST HAVE | M2.4 | Sanjana | Completed
Sprint3 | Sprint3 | US009 | Completeness Judge Agent | MUST HAVE | M3.1 | Sanjana | Completed
Sprint3 | Sprint3 | US010 | Weighted Scoring & Verdict Engine | MUST HAVE | M3.2 | Sanjana | Completed
Sprint3 | Sprint3 | US011 | Single Evaluation Result View & Explanation | MUST HAVE | M3.3 | Sanjana | Completed
Sprint3 | Sprint3 | US012 | Batch CSV Evaluation & Statistics | MUST HAVE | M3.4 | Sanjana | Completed
Sprint4 | Sprint4 | US013 | Evaluation Scoring Dashboard with Visual Analytics | MUST HAVE | M4.1 | Sanjana | Completed
Sprint4 | Sprint4 | US014 | Structured PDF Report Export via ReportLab | MUST HAVE | M4.2 | Sanjana | Completed
Sprint4 | Sprint4 | US015 | Full-Stack Cloud Deployment (Render & Streamlit Cloud) | MUST HAVE | M4.3 | Sanjana | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US005 | M2-T01 | Implement Relevance Judge Agent | 2026-09-14 | 2026-09-14 | Sanjana | Development | Completed | 4 | Day 1: 4
US006 | M2-T02 | Implement Accuracy Judge Agent with reference and evidence support | 2026-09-14 | 2026-09-14 | Sanjana | Development | Completed | 6 | Day 1: 6
US007 | M2-T03 | Implement claim-level Hallucination Detection Agent | 2026-09-14 | 2026-09-14 | Sanjana | Development | Completed | 6 | Day 1: 6
US008 | M2-T04 | Create Milestone 2 benchmark evaluation set and validate agent behavior | 2026-09-14 | 2026-09-14 | Sanjana | Testing | Completed | 4 | Day 1: 4
US008 | M2-T05 | Run full regression test suite and verify Milestone 2 integration | 2026-09-14 | 2026-09-14 | Sanjana | Testing | Completed | 3 | Day 1: 3
US009 | M3-T01 | Implement Completeness Judge Agent with aspect coverage | 2026-09-16 | 2026-09-17 | Sanjana | Development | Completed | 6 | Day 1: 6
US010 | M3-T02 | Implement weighted scoring and verdict aggregation | 2026-09-16 | 2026-09-17 | Sanjana | Development | Completed | 5 | Day 1: 5
US011 | M3-T03 | Integrate complete single evaluation result and explanations in UI | 2026-09-16 | 2026-09-17 | Sanjana | Development | Completed | 4 | Day 1: 4
US012 | M3-T04 | Implement batch CSV evaluation module and statistics | 2026-09-16 | 2026-09-17 | Sanjana | Development | Completed | 6 | Day 1: 6
US012 | M3-T05 | Execute Milestone 3 test suite and batch performance verification | 2026-09-16 | 2026-09-17 | Sanjana | Testing | Completed | 3 | Day 1: 3
US013 | M4-T01 | Build Evaluation Scoring Dashboard with dimension metrics and charts | 2026-10-14 | 2026-10-15 | Sanjana | Development | Completed | 6 | Day 1: 6
US014 | M4-T02 | Implement structured PDF report export with ReportLab | 2026-10-14 | 2026-10-15 | Sanjana | Development | Completed | 5 | Day 1: 5
US015 | M4-T03 | Deploy FastAPI backend to Render with memory-efficient vector backend | 2026-10-14 | 2026-10-15 | Sanjana | DevOps / Deployment | Completed | 5 | Day 1: 5
US015 | M4-T04 | Deploy Streamlit UI to Streamlit Community Cloud and link live API | 2026-10-14 | 2026-10-15 | Sanjana | DevOps / Deployment | Completed | 4 | Day 1: 4
US015 | M4-T05 | Perform end-to-end cloud validation, smoke testing, and dimension safeguards | 2026-10-14 | 2026-10-15 | Sanjana | Testing | Completed | 3 | Day 1: 3

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint2 | Milestone 2 | No blocking impediment during implementation and testing. | Implemented and tested Relevance, Accuracy, Hallucination agents and Milestone 2 benchmark validation.
Sprint3 | Milestone 3 | Batch CSV processing performance on larger datasets. | Implemented optimized batch loop and validated with multiple test CSV files.
Sprint4 | Milestone 4 | Render 512MB RAM limitation and vector dimension mismatch during deployment. | Optimized vector backend using stateless HashingVectorizer and deployed successfully on Render & Streamlit Cloud.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint1 | 2026-08-26 | 2026-08-26 | Sanjana | Understand requirements clearly before development | Starting development without reviewing requirements | Requirement analysis and planning | Reviewed Milestone 1 requirements and planned implementation
2 | Sprint1 | 2026-08-27 | 2026-08-27 | Sanjana | Study evaluation concepts before implementation | Relying only on assumptions | Researching LLM evaluation concepts | Studied relevance, factuality, hallucination and completeness
3 | Sprint1 | 2026-08-28 | 2026-08-28 | Sanjana | Design the architecture before coding | Making implementation changes without architecture planning | Maintaining architecture documentation | Designed the evaluation architecture and documented the system flow
4 | Sprint1 | 2026-08-29 | 2026-08-29 | Sanjana | Define clear responsibilities for each agent | Mixing responsibilities between agents | Using specialized evaluation agents | Defined responsibilities for the evaluation agents
5 | Sprint1 | 2026-08-31 | 2026-08-31 | Sanjana | Validate retrieved evidence before evaluation | Using unrelated retrieved information | Testing retrieval quality | Built and validated the RAG knowledge base
6 | Sprint1 | 2026-09-01 | 2026-09-02 | Sanjana | Test components during development | Waiting until the end to test | Running automated tests regularly | Added and executed automated project tests
7 | Sprint1 | 2026-09-02 | 2026-09-03 | Sanjana | Review evaluation results and improve the system | Ignoring unexpected evaluation results | Iterative testing and improvement | Reviewed Milestone 1 results and improved the evaluation pipeline
8 | Sprint2 | 2026-09-14 | 2026-09-14 | Sanjana | Continue structured agent testing and benchmark-based validation | Avoid making changes without running the relevant tests | Develop locally in VS Code, validate with pytest, and document completed Agile work | Milestone 2 agents and 19-test regression suite validated successfully
9 | Sprint3 | 2026-09-16 | 2026-09-17 | Sanjana | Structure batch evaluations with robust error fallbacks | Allowing unhandled format errors in uploaded CSVs | Comprehensive edge case testing | Added bad-format CSV validation and regression testing
10 | Sprint4 | 2026-10-14 | 2026-10-15 | Sanjana | Design cloud microservices with minimal memory footprints | Assuming cloud free tiers have unlimited RAM | Continuous Deployment via GitHub with automated testing | Deployed production architecture across Render and Streamlit Cloud with zero-downtime CI/CD