## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sanjana | 2026-09-02 | Backend server could not start because the Uvicorn module path was incorrect. | Sprint 1 | Sanjana | Configuration / Backend | Corrected the Uvicorn command to use the correct application module path. | 2026-09-03 | Closed | Backend started successfully after correcting the module path.
2 | Sanjana | 2026-09-03 | Evaluation request failed during the relevance filter while processing the AI response. | Sprint 1 | Sanjana | Backend/Evaluation | Debugged the evaluation pipeline and corrected the backend configuration/code. | 2026-08-05 | Closed | Evaluation pipeline was tested again after the fix.
3 | Sanjana | 2026-10-14 | Streamlit Cloud deployment threw ModuleNotFoundError: No module named reportlab. | Sprint 4 | Sanjana | Deployment / Dependency | Added reportlab and pandas to requirements.txt and pushed to GitHub main.
4 | Sanjana | 2026-10-14 | Render backend deployment crashed with Out of Memory (over 512MB) when loading PyTorch CUDA libraries. | Sprint 4 | Sanjana | Cloud / Performance | Switched default embedding backend to lightweight CPU/stateless hashing vectorization to operate under 60MB RAM.
5 | Sanjana | 2026-10-15 | Evaluation API failed with ValueError matmul core dimension mismatch (size 5 vs 101) during similarity search. | Sprint 4 | Sanjana | Backend / Logic | Unified vectorization using fixed 1024-dimension HashingVectorizer and added dimension slice protection in cosine_similarity.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others